## Sheet1
Task Description | Start Date | Completion Date | Milestone Completion Date
Specify Game Mechanics | 2023-10-08 | 2023-10-14
Develop Game Prototype | 2023-10-15 | 2023-10-28
Integrate Unity and RL Framework | 2023-10-29 | 2023-11-11
Design RL Agent Architecture | 2023-11-12 | 2023-11-25
Implement RL Agent | 2023-11-26 | 2023-12-23
Create Training Environment | 2023-12-24 | 2024-01-13
Define Training Scenarios | 2024-01-14 | 2024-01-27
Train RL Agent | 2024-01-28 | 2024-02-03
Evaluate RL Agent | 2024-02-04 | 2024-02-10
Refine Game Mechanics | 2024-02-11 | 2024-02-17
Enhance Game Features | 2024-02-18 | 2024-03-02
Update RL Agent | 2024-03-03 | 2024-03-16
Test Gameplay Experience | 2024-03-17 | 2024-04-13
Document Project Progress | 2023-10-08 | 2024-04-13
Project Presentation and Reporting | 2024-03-31 | 2024-04-13