## Sheet1
Task Description | Primary Responsibility | Grant Fullenkamp (Project Supervisor) | Trevor Darst (Game Developer) | Roshan Krishnan (Machine Learning Engineer) | Noah Hienen (Game Designer/Software Engineer)
Specify Game Mechanics | Noah Hienen (Game Designer) | 30% | 20% |  | 50% | 100%
Develop Game Prototype | Trevor Darst (Game Developer) | 20% | 60% | 10% | 10% | 100%
Integrate Unity and RL Framework | Noah Heinen (Software Engineer) | 20% | 20% |  | 60% | 100%
Design RL Agent Architecture | Roshan Krishnan (Machine Learning Engineer) | 30% | 20% | 50% |  | 100%
Implement RL Agent | Roshan Krishnan (Machine Learning Engineer) | 30% | 10% | 60% |  | 100%
Create Training Environment | Trevor Darst (Game Developer) | 20% | 60% | 10% | 10% | 100%
Define Training Scenarios | Noah Hienen (Game Designer) | 20% | 20% |  | 60% | 100%
Train RL Agent | Roshan Krishnan (Machine Learning Engineer) | 30% | 10% | 50% | 10% | 100%
Evaluate RL Agent | Roshan Krishnan (Machine Learning Engineer) | 30% | 10% | 60% |  | 100%
Refine Game Mechanics | Noah Hienen (Game Designer) | 20% | 20% |  | 60% | 100%
Enhance Game Features | Trevor Darst (Game Developer) | 20% | 60% | 20% | 10% | 110%
Update RL Agent | Roshan Krishnan (Machine Learning Engineer) | 30% | 10% | 60% |  | 100%
Test Gameplay Experience | Noah Hienen (Game Designer) | 30% | 10% | 10% | 50% | 100%
Document Project Progress | Grant Fullenkamp (Project Supervisor) | 50% | 15% | 15% | 20% | 100%
Project Presentation and Reporting | Grant Fullenkamp (Project Supervisor) | 50% | 15% | 15% | 20% | 100%
|  | 430% | 360% | 360% | 360%
| Total Effort (%/20 = Hours): | 86 | 72 | 72 | 72